## Team Members
Enter the First Name of Each Team Member | HOW TO USE: | 1. File Menu --> Make a copy
Sam |  | 2. Save to one team member's Google drive
Connor |  | 3. Share file with other team members
Alex |  | 4. Edit First Names on this tab
Adam |  | 5. Add your team name to the name of this document
Lucas |  | 6. For each sprint, duplicate the sprint template and change the start date
DOCUMENT HISTORY
| 2017-09-20 | Created by Justin Sybrandt (http://sybrandt.com/post/google-slides-agile/)
| 2019-03-23 | Modified by Susanne Sherba for use in COMP 3381 (Software Engineering I)

## Sprint Template (Make a copy!)
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
[5 empty] | To Do |  | Sprint Number: | 0 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2019-03-30 | 0 | 0 | 0 | 0
[5 empty] | To Do |  | Start Date: | 2019-03-30 | Sam | 0 | 0 | 0% | 2019-03-31 | 0 | 0 | 0 | 0
[5 empty] | To Do |  | Sprint Length | 14 | Connor | 0 | 0 | 0% | 2019-04-01 | 0 | 0 | 0 | 0
[5 empty] | To Do |  | Hours Per Day: | 0 | Alex | 0 | 0 | 0% | 2019-04-02 | 0 | 0 | 0 | 0
[5 empty] | To Do |  |  |  | Adam | 0 | 0 | 0% | 2019-04-03 | 0 | 0 | 0 | 0
[5 empty] | To Do |  |  |  | Lucas | 0 | 0 | 0% | 2019-04-04 | 0 | 0 | 0 | 0
[5 empty] | To Do |  |  |  |  | 0 | 0 | 0% | 2019-04-05 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-06 | 0 | 0 | 0 | 0
[5 empty] | To Do |  |  |  | Total: | 0 | 0 | 0% | 2019-04-07 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-08 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-09 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-10 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-11 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-12 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-13 | 0 | 0 | 0 | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Chart Dates = if(and(ISDATE([Chart Dates, row above]),[Chart Dates, row above]-J3<J4), [Chart Dates, row above]+1, "")
Current Remaining Work = if([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")

## Product Backlog
Sprint Number | User Story ID | User Story Title | Brief Description | Additional Information | Priority | Status
1 | 1 | CURESORT query response time | A user of CURESORT, should be able to look up an item quickly, so that they can put that item in the correct bin and not waste valuable time. | A significant lag time on queries can be possibly fixed by optimizing CURESORT code, thus making it more efficient. | 1-high | In Progress
1 | 2 | Admin access for CURESORT | An Admin of CURESORT, should be able to add other sub-admins, so that they can also have admin access control. | The ability to add other admins to CURESORT, without having to manually put them in by accesing the backend of CURESORT | 3-low | To Do
1 | 3 | Flagging system |  |  | 3-low | Done
2019-01-02 | 4 | Check the Database as Admin | An Admin of CURESORT would like to be able to check the updates every week of the database, so that they can make sure the items are input correctly |  | 3-low | To Do
2019-01-02 | 5 | Search Quality | A user of CURESORT would like to be able to search as generally as possible and still have the correct item show up. For example, John Smith may not pull up the requested item, but John will. Both should pull up "John" | Is this maybe because of the way in which the search is being conducted? Is there a way we can allow for more specific and more general key terms to bring up the same things? | 1-high | In Progress
2019-01-02 | 6 | Be able to search not based on barcode | A user of CURESORT should be able to search an item using some other keyword then just its barcode so that they can still find the item even if the scanner doesn't work | The book system (to look up items) seems to take a long time... Is there a way we can make a "Did you mean...?" in the search term to better guide volunteers? | 1-high | To Do
2019-01-02 | 7 | Look at the Database Tables | An admin of CURESORT would like to be able to check the tables of the database so that they can see potential duplicates of the items there | Admins would like the ability to actually see what is going on in the database... Way to check on tables etc. | 3-low | To Do
2019-01-02 | 8 | Old scanning system | A user of CURESORT would like to make sure they are using the right version of CURESORT in order to spend their time wisely | Sometimes the old CURESORT will pop up of the systems instead of the new ones and volunteers will have to restart the system | 3-low | To Do
2019-01-02 | 9 | Search Guide | A volunteer of CURESORT would like to be able to search the CURESORT system with the most effective keywords in order to find the bin number and item they are looking for | The system is hard for newcomers to pick up quickly. Norma, a 12 year volunteer with Project CURE, said that it's still difficult for her after so long to search the system correctly. In a way its like using Google, you have to know the best key terms to use in order to get back what you want. Maybe making a booklet or something that walks users through how to search through the system would be really helpful? What key terms to use and how to go about looking for an item? This would ensure that volunteers are using their time the most effectively they can | 1-high | To Do
| 10 | Usability | A user of CURESORT would like to be able to read the results of their search and see buttons more clearly so they don't have to strain their eyes to see instructions | The font size and buttons are a little user unfriendly. This is more user design then anything but would help make the system more user friendly as a lot of people are using it every day | 3-low | To Do
| 11 | Flagging system | A user of CURESORT should know how to use the flagging system to help flag items that should (or shouldn't) be in the system | We realized that the flagging system is actually already in CURESORT, but a lot of the users don't know how to use it. This may be another guide that we write up so that users actually understand how to use this feature of the system. I spoke with a volunteer and he said he hand't learned of the system until a few days ago and has been working at Project CURE for 10 years. He said it took him 3 minutes to learn. | 3-low | Done
| 12 | Installation of Database | A designer (updater) of CURESORT would like to be able to install the database and run it locally on their own machine to be able to test the software | It's been a lot of trouble getting the system up on running locally on our machine. I think that creating a guide to help out the next team get along quicker would be extremely helpful. | 2-medium | Done
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 1-high | To Do
[5 empty] | 2-medium | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do

## Sprint 1 419 - 52
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
| Talk to Nate about Azure DTUs | 1 | 0.5 | Connor | Done | 2019-04-19 | Sprint Number: | 0 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2019-04-19 | 2.1 | 2.1 | 20.1 | 22.2
| Talk to Nate about Azure DTUs | 1 | 0.5 | Adam | Done | 2019-04-19 | Start Date: | 2019-04-19 | Sam | 4.4 | 0.4 | 9.091% | 2019-04-20 | 0 | 2.1 | 20.1 | 20.6143
| Analyze Azure data | 1 | 2 | Connor | Done | 2019-04-30 | Sprint Length | 14 | Connor | 5.4 | 2.4 | 44.44% | 2019-04-21 | 0 | 2.1 | 20.1 | 19.0286
| Write up summary about data / compress | 1 | 2 | Adam | Done | 2019-04-30 | Hours Per Day: | 1.5857 | Alex | 4.6 | 0.6 | 13.04% | 2019-04-22 | 0 | 2.1 | 20.1 | 17.4429
| Video Call to chat with Tim | 0.4 | 0.5 | Lucas | Done | 2019-04-26 |  |  | Adam | 4.4 | 2.4 | 54.55% | 2019-04-23 | 0 | 2.1 | 20.1 | 15.8571
| Video Call to chat with Tim | 0.4 | 0.5 | Sam | Done | 2019-04-26 |  |  | Lucas | 3.4 | 0.4 | 11.76% | 2019-04-24 | 0 | 2.1 | 20.1 | 14.2714
| Link Statement Explanation | 1 |  | Adam | To Do |  |  |  |  | 0 | 0 | 0% | 2019-04-25 | 0 | 2.1 | 20.1 | 12.6857
| Video Call to chat with Tim | 0.4 | 0.5 | Adam | Done | 2019-04-26 | [6 empty] | 2019-04-26 | 1.6 | 3.7 | 18.5 | 11.1
| Video Call to chat with Tim | 0.4 | 0.5 | Connor | Done | 2019-04-26 |  |  | Total: | 22.2 | 6.2 | 27.93% | 2019-04-27 | 0 | 3.7 | 18.5 | 9.5143
| Email Tania with survey | 0.1 | 0.1 | Alex | Done | 2019-04-19 | [6 empty] | 2019-04-28 | 0.5 | 4.2 | 18 | 7.9286
| Link Statement Location | 1 |  | Alex | To Do | [7 empty] | 2019-04-29 | 0 | 4.2 | 18 | 6.3429
| Run Code on Local Machines | 1 | 2 | Sam | In Progress | [7 empty] | 2019-04-30 | 2 | 6.2 | 16 | 4.7571
| Run Code on Local Machines | 1 | 5 | Connor | In Progress | [7 empty] | 2019-05-01 | 0 | 6.2 | 16 | 3.1714
| Run Code on Local Machines | 1 | 2 | Alex | In Progress | [7 empty] | 2019-05-02 | 0 | 6.2 | 16 | 1.5857
| Run Code on Local Machines | 1 | 3 | Adam | In Progress | [7 empty] | 2019-05-03 | 0 | 6.2 | 16 | 0
| Run Code on Local Machines | 1 | 3 | Lucas | In Progress | [8 empty] | 0 | 4.1 |  | 0
| Email Tania about next meeting | 0.5 | 0.5 | Alex | Done | 2019-04-28 | [7 empty] | 0 | 4.1 |  | 0
| .NET Tutorials | 2 |  | Connor | To Do | [8 empty] | 0 | 4.1 |  | 0
| .NET Tutorials | 2 |  | Sam | To Do | [8 empty] | 0 | 4.1 |  | 0
| Convert Email Responses to User Stories | 1 | 3 | Sam | In Progress | [8 empty] | 0 | 4.1 |  | 0
| Review postgreSQL aspects for CURESORT | 2 |  | Lucas | In Progress | [8 empty] | 0 | 4.1 |  | 0
| Review postgreSQL aspects for CURESORT | 2 |  | Alex | In Progress | [8 empty] | 0 | 4.1 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 2.5 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 2.5 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 2 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 2 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Chart Dates = if(and(ISDATE([Chart Dates, row above]),[Chart Dates, row above]-J3<J4), [Chart Dates, row above]+1, "")
Current Remaining Work = if([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")

## Sprint 2 52-516
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
5 | Search Generality | 2 |  | Alex | In Progress |  | Sprint Number: | 0 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2019-05-02 | 0 | 0 | 21 | 21
9 | Search Guidelines | 1 |  | Sam | To Do |  | Start Date: | 2019-05-02 | Sam | 3 | 2 | 66.67% | 2019-05-03 | 0 | 0 | 21 | 19.5
| Installation Guide | 2 | 2 | Connor | Done | 2019-05-09 | Sprint Length | 14 | Connor | 9 | 9 | 100% | 2019-05-04 | 0 | 0 | 21 | 18
| Code Installation | 3 | 5 | Connor | Done | 2019-05-16 | Hours Per Day: | 1.5 | Alex | 5 | 0 | 0% | 2019-05-05 | 4 | 4 | 17 | 16.5
| Dotnet Tutorial | 2 | 1.5 | Connor | Done | 2019-05-05 |  |  | Adam | 2 | 2 | 100% | 2019-05-06 | 0 | 4 | 17 | 15
| Dotnet Tutorial | 2 | 1.5 | Sam | Done | 2019-05-05 |  |  | Lucas | 2 | 0 | 0% | 2019-05-07 | 0 | 4 | 17 | 13.5
| Archiving Guide | 2 |  | Lucas | In Progress |  |  |  |  | 0 | 0 | 0% | 2019-05-08 | 0 | 4 | 17 | 12
| Archiving Guide | 2 |  | Alex | In Progress | [7 empty] | 2019-05-09 | 2 | 6 | 15 | 10.5
3 | Flagging System | 2 | 1 | Connor | Done | 2019-05-16 |  |  | Total: | 21 | 13 | 61.9% | 2019-05-10 | 0 | 6 | 15 | 9
3 | Flagging System | 2 | 1 | Adam | Done | 2019-05-16 | [6 empty] | 2019-05-11 | 0 | 6 | 15 | 7.5
| Set up Tania meeting | 1 |  | Alex | In Progress | [7 empty] | 2019-05-12 | 0 | 6 | 15 | 6
[5 empty] | To Do | [7 empty] | 2019-05-13 | 0 | 6 | 15 | 4.5
[5 empty] | To Do | [7 empty] | 2019-05-14 | 0 | 6 | 15 | 3
[5 empty] | To Do | [7 empty] | 2019-05-15 | 0 | 6 | 15 | 1.5
[5 empty] | To Do | [7 empty] | 2019-05-16 | 7 | 13 | 8 | 0
[5 empty] | To Do | [8 empty] | 0 | 13 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 13 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 13 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 9 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 9 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 9 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 9 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 7 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 7 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 7 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 7 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 7 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 7 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 7 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Chart Dates = if(and(ISDATE([Chart Dates, row above]),[Chart Dates, row above]-J3<J4), [Chart Dates, row above]+1, "")
Current Remaining Work = if([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")

## Sprint 3 517 - 530
2019-05-17 | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
| Archiving Guide | 2 | 2 | Alex | Done | 2019-05-30 | Sprint Number: | 0 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2019-05-17 | 0 | 0 | 15 | 15
| Archiving Guide | 2 | 2 | Lucas | Done | 2019-05-30 | Start Date: | 2019-05-17 | Sam | 2 | 2 | 100% | 2019-05-18 | 0 | 0 | 15 | 13.8571
| Set up Tania meetings | 2 | 1 | Alex | Done | 2019-05-29 | Sprint Length | 14 | Connor | 2 | 2 | 100% | 2019-05-19 | 1 | 1 | 14 | 12.7143
| Flagging System | 2 | 0.5 | Connor | Done | 2019-05-23 | Hours Per Day: | 1.1429 | Alex | 6 | 4 | 66.67% | 2019-05-20 | 0 | 1 | 14 | 11.5714
| Flagging System | 2 | 0.5 | Adam | Done | 2019-05-23 |  |  | Adam | 3 | 3 | 100% | 2019-05-21 | 0 | 1 | 14 | 10.4286
| Error Messages | 1 |  |  | To Do |  |  |  | Lucas | 2 | 2 | 100% | 2019-05-22 | 0 | 1 | 14 | 9.2857
| Usage Guide | 2 | 1 | Sam | Done | 2019-05-30 |  |  |  | 0 | 0 | 0% | 2019-05-23 | 4 | 5 | 10 | 8.1429
| Wildcard | 2 |  | Alex | In Progress | [7 empty] | 2019-05-24 | 0 | 5 | 10 | 7
| Test Installation Guide / Write Up | 1 | 1 | Adam | Done | 2019-05-19 |  |  | Total: | 15 | 13 | 86.67% | 2019-05-25 | 0 | 5 | 10 | 5.8571
[5 empty] | To Do | [7 empty] | 2019-05-26 | 0 | 5 | 10 | 4.7143
[5 empty] | To Do | [7 empty] | 2019-05-27 | 0 | 5 | 10 | 3.5714
[5 empty] | To Do | [7 empty] | 2019-05-28 | 0 | 5 | 10 | 2.4286
[5 empty] | To Do | [7 empty] | 2019-05-29 | 2 | 7 | 8 | 1.2857
[5 empty] | To Do | [7 empty] | 2019-05-30 | 6 | 13 | 2 | 0.14286
[5 empty] | To Do | [7 empty] | 2019-05-31 | 0 | 13 | 2 | 0
[5 empty] | To Do | [8 empty] | 0 | 13 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 13 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 12 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 12 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 12 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 12 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 8 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 8 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 8 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 8 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 8 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 8 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 6 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Chart Dates = if(and(ISDATE([Chart Dates, row above]),[Chart Dates, row above]-J3<J4), [Chart Dates, row above]+1, "")
Current Remaining Work = if([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")